## Sheet1
Story ID | Story Name | Story | Priority | Iteration number | Acceptance Criteria | Notes | Date started | Date finished
E01a | Add new customer | As a Bank Employee, I want to obtain customers' details like: name, addresses and date of birth. And I can enter the details to the system. So that I can add new customer to the system. | 1 | 1 | verify that the customer does not exist in system |  | 14/3/2017 | 19/3/2017
E01b | Open account | As a Bank Employee, I want to enter the Customer's details and account type in the system along with the opening deposit, so that I can open an account for the customer. | 1 | 1 | Verify that the customer does not exist in the system. |  | 20/3/2017 | 22/3/2017
E01c | Open Saver Account | As a customer, I want to open a saver account, So that I can deposit money to my account. | 1 | 2 | 1. Verify that the customer does not exist in the system. |  | 20/3/2017 | 22/3/2017
E01d | Open Current Account | As a customer, I want to open a current account, so that I can withdraw more funds than the limit which will not exceed the overdraft limit. | 1 | 2 | 1.Verify that the customer does not exist in the system. 2. Verify the overdraft limit is decided. |  | 20/3/2017 | 22/3/2017
E01e | Open Junior Account | As a customer whose age is under 16, I want to open a junior account, so that I can own a account as adults. | 1 | 2 | 1.Verify that the customer does not exist in the system. 2. Verify the customer is not above 16 years old. |  | 20/3/2017 | 22/3/2017
E01f | Create account | As a Bank Employee, I want to create an account of the type chosen for an existing customer, generate a unique account number and PIN. So that I can open the account and notify customer of account number and PIN. | 1 | 1 | 1. Verify that customer exists in system matching details given 2. Make sure that customer's credit status has been recorded as satisfactory 3. Verify that account of required type is created 4. Verify that account number is unique 5. Verify that PIN is 6 digits |  | 20/3/2017 | 22/3/2017
E02 | Deposit | As a depositor， I want to enter the details of the account to be credited and the amount of funds to be deposited. So that I can deposit the funds to the account. | 2 | 2 | 1. Verify that account exists matching account number 2. Verify that the account is not inactive or suspended, otherwise return funds to depositor 3. Make sure that an receiptis issued to depositor |  | 24/3/2017 | 1/4/2017
E03 | Account type | As a customer, I wan to choose the account type that I want to open such as： saver account, junior account and current account, so that I can have an account which is suitable for my need. | 2 | 1 | 1.Verify that the chosen account type is among the saver, junior and current accounts. |  | 3/4/2017 | 10/4/2017
E04 | Clear Funds | As an external bank clearing system, I want periodically clears un-cleared funds. So that the funds are credited to the account. | 3 | 2 | 1. Verify that there exists un-cleared funds. |  | 12/4/2017 | 15/4/2107
E05 | Withdraw Funds | As a customer, I want to supply my account number, the correct PIN, and the amount to be withdrawn. So that I can withdraw suitable amount of funds from my account. | 3 | 2 | 1. Verify that the money that the customer want to withdraw is no more than the sum of balance and overdraft limit. |  | 16/4/2017 | 20/4/2017
E06 | Suspend Account | As a Bank Employee, I want to supend an account. So that no further transactions or operations may occure until the account is re- instated. | 3 | 3 | 1. Verify the account exists. 2. Verify the suspending account number is correct |  | 22/4/2017 | 25/4/2017
E07 | Set Notice Date | As a Bank Employee, I want to confirm a minimum period of notice (in days) must be given before any withdrawal can be made So that I can withow money before that day | 3 | 3 | 1. Verify the account is saver account. |  | 26/4/2017 | 30/4/2017
E08 | Close Account | As a Bank Employee, I want to check if the account balance is zero when I receive the instruction from the customer to close the account. So that I can close the account. | 3 | 3 | 1. Verify the account is not used anymore. 2. Verify the account number of the account which would be closed is correct. |  | 30/4/2017 | 1/5/2017